## Slide 1
Community Systems Strengthening Project Implementation
APPLICANTS WELFARE DEVELOPMENT CENTER(AWANDEC)

## Slide 2
Synopsis:
22/04/2022
2
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
1
2
3
4
5
6
Overview of specific CSO Community systems strengthening FY’22 Targets and Expected deliverables
Summary of Achievements and strategies employed
Birth Registration target, achievements against targets and plans to the excess if any
CIT implementation, key achievements and plans
LGA engagements strategies and plans
Where you need support
7
What do you want change in the way CCCRN supports you
8
Key pending activities

## Slide 3
Overview of specific CSO Community systems strengthening FY’21 Targets and Expected deliverables
22/04/2022
3
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
Targets | Expected deliverables
Set-up at least 6 CQIT/CITs/CPC and conduct capacity assessment for existing ones to promote community participation in OVC program implementation and monitoring | Reactivate existing/set up 6 CPC/CQIT in 4 LGAs
Facilitate access to Birth registration and Birth certificate issuance to children without Birth certificate | Ensure 1200 and more OVC are provided birth certificate
Set-up and hold quarterly meeting with LGA Coordination Task Team | Hold CIT meetings in 2 LGAs
Conduct mapping of community structures and update the community- facility entry points/referral directory e.g. TBA/FBA/Community clinics etc in Project LGAs | Map TBA/FBA within coverage areas, get contact details, attend meetings and provide HTS support
Conduct at least 3 Community dialogue sessions on HIV/AIDS related stigma reduction, child protection and gender knowledge sessions during through community structures | Engage with stakeholders in 3 communities across 3 LGAs for dialogue sessions

## Slide 4
Summary of Achievements and strategies employed
22/04/2022
4
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
Achievements | Strategies employed
Facilitated the provision of birth certificates for 102 OVC | Form B1 was issued to the CCWs for registration The completed form B1 was given to NPOPc for registration Form B2 was retrieved from NPOPc and given to CCWs CCWs and CSS staff issued the form B2 to caregivers
Set-up and following up on 2 CPC for two communities | Advocacy visit to village for debrief and consent Mobilized stakeholders through the CCW and scheduled a meeting Inauguration and orientation of CPC group Follow up monthly meetings
Held two community learning hub sessions | Identified CCWs with Educational background and motivated them to carry out the activity.
Mapped community entry point (194 TBA facilities, 2 FBA,8 PPMV,4 COMMUNITY CLINICS) | Identification of TBA facilities, FBA, PPMV and COMMUNITY CLINICS through CCWs
Re-enrollment of out of school OVC | CPC supported identification and re-enrollment of out of school children through PPP

## Slide 5
Birth Registration target VS achievements against target and plans
BIRTH REGISTRATION | TARGET | ACHIEVEMENT
1200 | 1200 | 102
PLANS/WAYFORWARD | Registration and issuance of 800 birth certificates by May 2022 and 1200 by July 2022 through the CCWs during home visit in collaboration with NPOPc

## Slide 6
Community Dialogue implementation, key achievements and plans
22/04/2022
6
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
S/N | KEY ACHIEVEMENT | PLANS
1 | Identified and carried out community dialogue at ANUA and AWAT | Schedule meeting date with stakeholders for session during council meetings
2 |  | 

## Slide 7
LGA engagements strategies and plans
22/04/2022
7
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
Meeting with SWOs to schedule date for coordination meeting between May and June 2022

## Slide 8
Where you need support
22/04/2022
8
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
Incentives for key community activities

## Slide 9
What do you want change in the way CCCRN supports you
22/04/2022
9
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
Timely approval of workplan and release of funds

## Slide 10
Key pending activities
22/04/2022
10
CENTER FOR CLINICAL CARE AND RESEARCH NIGERIA
LGA assessment at URUE OFFONG AND UDUNG UKO

## Slide 11
Integrated Child Health and Social Services Award (ICHSSA Lot 1) is a five-year cooperative agreement funded by the U.S. President’s Emergency Plan for AIDS Relief through the U.S. Agency for International Development under Agreement No. 72062020CA00006, beginning December 19, 2019. It is implemented by Center for Clinical Care and Research Nigeria, in partnership Catholic Relief Services, and supported by expert local resource partners.
This presentation was produced for review by the U.S. President’s Emergency Plan for AIDS Relief through the United States Agency for International Development. The information provided [in this document] is not official U.S. government information and does not necessarily reflect the views or positions of the U. S. President’s Emergency Plan for AIDS Relief, U.S. Agency for International Development or the United States Government.