YOUTH ALIVE FOUNDATION, UYO

MINUTES OF MEETING HELD.

E.U Project ( Reducing Digital Gender Gaps in The Niger Delta)

10th May 2023

| ATTENDANCE | AGENDA |
| --- | --- |
| Kingsley Atang | Updates, Strategy and Planning Session on the E.U project. |
| Chamberlain |  |
| Onyeka Ajah |  |
| David Williams |  |
| Kornom A |  |

The meeting started at about 7:30pm. Kingsley Atang welcomed everyone to the meeting. Onyeka continued by asking Emanuel to give a brief summary and update on the E.U Project.

UPDATE ON E.U PROJECT

Emmanuel reporting on the project reported that Fliers and hand bills has been circulated and it’s still ongoing on social media platforms, radio jingle has been produced and aired, 130 registration forms have been printed and

Kingsley pointed out the importance of engaging with Government of Akwa ibom State, map out stake holders that would give more feasibility and engage them on the benefits their constituents stand to enjoy if they enroll in the program. He also added that he is waiting for the report of the research because it will help in our discussion with government agencies so when they role out projects our questions would be what is the quota for women in their projects and planning? This will give YAF good will whenever YAF approaches them for anything it would be easy for them to resonate with YAF. He also warned to  be careful of the individual so that they don’t politicize it, he also laid emphasis on the quality of persons we want to accept from stakeholders to be trained. Finally he asked how would we curb truancy during the training.

Onyeka informed the team that anyone that misses for more than two in a week would not get complete stipend.

Chamberlain updated the team that registrations end on the 19th of May 2023 and we are moving to the next phase of the project which is selection and batching of the beneficiaries. He pointed out that we need to know the number of business women and private individuals in a particular batch. He further added that with 25 dollars shared spent so far we have had more than 300 applicants and we would get more than 600 applicants. He stated that there would be lot of work because men are applying for the training and plans should be put in place for batching and selection. Chamberlain added that the essence of batching is to put them in their learning categorizes.

Onyeka added that beneficiaries are required to be trained on one course for three months even though they were given an option to select three top courses of their choice. Onyeka pointed out that if we were to take all the courses there won’t be centers for them. She also added that Ifeoma hinted the facilitator would prepare the course manual.

David added we should engage the facilitators on the number of hours per day which would inform us on the number of courses that can be taken in a day.

Chamberlain further added that the needs assessment guides the reasons why YAF picked certain courses for the beneficiaries.

Kingsley reminded the team of partnership which would help YAF draw SAVINGS from the project. He also added that seeking partnership with our ICT friends would help save cost, we also need to tell them areas where we require their support with facility, linking beneficiaries to Internship opportunities and other packages.

Chamberlain suggested that we could do a Media Event for the Unveiling and start off the training which he had discussed with the Executive director. We would invite relevant stakeholders in Government,  public  and private enterprise. He also added there would be a key note speaker.

AOB

Task for the Week

UYO team

- Mapping  and Engagement of Stakeholders.

- Plan and prepare for a Media Event (Unveiling of the beneficiaries) for the E.U project.

- Assign two persons to explore e-library as an option for the training.

Chico

- Reach out to Umo Eno’s daughter  for engagement for the project.

Emmanuel

- Create a system for filtering the applicants.

- Plan and prepare budget  for a Media Event (Unveiling of the beneficiaries) for the E.U project.

Onyeka

- Follow up with Hanson on the batching ratio.

David

- Follow up Chico on Umo Eno’s daughter  contact.

Kornom

- Support Emmanuel in budgeting for the media event.

The meeting ended at about 10:45am with Kingsley moving the motion for adjournment seconded by David.