Integrated Child Health and Social Service Award (ICHSSA 1)

Community System Strengthening Report

Quarter 2/2022

| State: | AKWA IBOM |
| --- | --- |
| CSO | APPLICANTS WELFARE DEVELOPMENT CENTER |
| Reporting Period: | # JAN-MARCH |
| Report Type (monthly, quarterly) | # QUARTELY |
| Submitted by: (Name and designation) | # AKPAN, EMMANUEL NDIFREKE . # COMMUNITY SYSTEM STRENGTHENING / GENDER OFFICER |
| Submission date: | # 31/3/2023 |

- Executive Summary. (This should be a brief summary of all your monthly/quarterly achievement in bullet points)

- AWANDEC in the month of February facilitated the provision of 200 birth certificate to 200 OVC across her four implementation LGAs. Form B1 were distributed to AWANDEC’s Community Case Workers (CCWs) to capture the information/details of OVC in the project without Birth Certificates. These form B1 were taken to the different communities across the implementation LGAs to obtain the necessary information concerning the OVC to be issued birth certificates. The filled form B1 were then forwarded to NPOPC for birth documentation and certification. The completed birth certificates were retrieved from NPOPC, photocopied and kept in the OVC’s household folders while the original certificates (form B2) were handed over to the beneficiaries (OVC) for their use. - In the month of January, AWANDEC inculcated Quality Improvement in Ekeya community in OKOBO LGA. The aim of the meeting was to introduce quality improvement to the members of the CPC in the targeted communities and as well enlighten the members on their responsibilities which will include identifying the needs of the vulnerable children, analyze the causes of the problems faced by the children, agreeing on changes to be made and meet regularly to evaluate progress. - AWANDEC is committed to driving policies that protect children in their various communities while strengthening existing community structures to help enhanced rights based approach in addressing child protection issues and ensuring the involvement of gatekeepers for safeguarding children from harm and abuse. Within the reporting month, AWANDEC held a dialogue session in OBUFI community in OKOBO LGA. The aim of the session was to discuss issues on Child Abuse and to solicit support from the Child Protection Committee members in addressing this issue.

- CSS Strategy(Report the strategies you used in carrying out your activities in bullet form)

- Birth registration was carried out for 200 vulnerable children.OVC without birth certificates were extracted from folder Audit. The tracked OVC were provided with form B1 which were correctly filled by AWANDEC’s Community Case Workers (CCWs) and returned to AWANDEC’S Sub-Office, Okobo. The completed Form B1 were taken to NPOPC for documentation and certification. The completed birth certificates were retrieved from NPOPC and photocopied. The photocopied birth certificates (form B2) were kept in the OVC’s household folders. While the original certificates (form B2) were handed over to the beneficiaries (OVCs) for their use.

- There was a need to incorporate  quality improvement into the activities and affairs of the Child Protection committee in Ekeya as the Chief mentioned that there are a lot of things to be done in Ekeya. The CSS officer met with CPC and explained to the essence of having a CQIT.

- Accomplishments during reporting period(describe activity title/type and achievements at output

Levels, without deleting any output not achieved for the period)

Output 1: Community leaders, members and traditional institutions utilize community instruments and existing structures to achieve reduction in HIV stigma and discrimination. (report CIT/CPC , dialogue sessions and STAR etc.activities and how it has contributed to HIV stigma and discrimination reduction in the community Community Structures (CIT/CPC): LGA; Total No of Existing CIT/CPC managed by CSO; No of Newly formed in the month/quarter; Name of Community with the new; No of CIT/CPC met within the month/quarter. OKOBO; 5; 0; 0; 1. MBO; 1; 0; 0; 0. UDUNG UKO; 2; 0; 0; 0. Activities and Actions Taken/Implemented Community Dialogue Sessions: Name of LGA/community; Issue Addressed/Discussed; No of Males; No of Females; Total in Attendance. Okobo/Obufi; Out of School Children; 5; 8; 13. - Actions agreed /Next Steps Societies Tackling AIDS through Rights(STAR)( Activity/Actions taken within the reporting period, follow on activities from previous activity/discussion, what support is required from CCCRN LGA TaskTeam Meeting: Name of LGA/community; Issue Addressed/Discussed; No of Males; No of Females; Total in Attendance. - Actions agreed /Next Steps Output 2: Communities advocate for and facilitate improved birth registration of children. (Report the effort made in getting birth certificate including, collaboration with government/ community, number of BC issued, number photocopied, entered into NOMIS, filed and delivered to CG, and the gap - Collaboration with Government/ Community # BC issued M f; # photocopied; # entered into NOMIS; # filed in the folders; # delivered to Caregivers; #Gap M f T. Output 3: Community leaders have improved knowledge of OVC rights, implement actions to protect and support children rights (Report activities you implemented that promote child rights, safeguarding and child protection.eg dialogue sessions, signing of safe guarding policy, community laws to promote child rights, cases of abuse/exploitation/GBV resolved/addressed/referred through community intervention) Output 4: Communities Develop Systems to Monitor Local Government Accountability(Report number of communities with systems to advocate, influence, monitor,and support OVC/HH by the LGAs, actions taken by the community to ensure LGAs responses, results from the actions, challenges and recommendations, materials required) Output 5: Local and state governments developed costed OVC Plans of Action for providing high quality services to protect and care for OVC(number of LGAs with costed work planand being implemented, No that have inaugurated QIT, No of QIT met in the period, Actions taken/Activity implemented, No/name of LGAs assessed in the period, support needed from CCCRN etc). Output 6: Financial resources mobilized from the public sector through allocation from local and state governments for OVC interventions(Report LGAs with budget line allocation for OVC, what was budgeted (one off reporting) and what was released to the LGA (monthly) to support OVC activities. S/N; Name of LGA; Year; Total Allocation/Appropriation (#); Amount Released (#) (Monthly). Output 7: Financial and non-financial resources mobilized to support Orphans and vulnerable children from private, community and non-USG sources(Report on your resource mobilization effort, strategies and achievement from public and private sectors and philanthropist. S/N; Name of LGA; Year/month; Resources Realized/Donated (Amount/ Items) if items state Naira equivalent after listing the items; Name of Institution/organization/ group/community; Need(s) to Address; Periodic/One-off Contribution (No: Yes) if yes state monthly, quarterly etc.

- Other Activities(Report any other activity not in the output mentioned  above e.g training, Assessment etc carried out within the report period

- Challenges and Lessons Learned / Way Forward

Document the challenges encountered during the reporting period, how you addressed them and the way forward for subsequent occurrence.

| Challenge | How you surmount the challenge | Way forward |
| --- | --- | --- |
| Low CSS activities carried out due to the cash less policy, delay in release of funds,elections and fuel hike. |  |  |
| . |  |  |

- Key Learnings( Report key lessons learned in carrying out specific activities and the results from these activities)

| What did you do | How you did it | What are the results | What did you learn |
| --- | --- | --- | --- |

- Success Stories/other Achievements/Results   (Report success obtained in the course of implementation.

- Plans for next reporting period

Provide a brief explanation of key activities planned for the next reporting period.

- Birth registration for children that have not been registered with NPOC. - Set up 2 CIT/CPC in Urue Offong - Participate in LGA QIT meeting in Mbo and Okobo.