YOUTH ALIVE STAFF MEETING May 2, 2023.

ATTENDANCE

Kayeon Onyeka

David Williams

Future Felix Ukeme

Chikodi Kingsley

Emmanuel Akpan

The meeting began with an opening prayer led by Kayeon Onyeka .Everyone took turns to share how their weekend went and also new lessons each person had from the previous week and tasks from previous week were reviewed.

UPDATES ON TASKS / ACTIVITIES

Updates on SAVE: David shared updates on which he provided the contact lawyer from STCC with a soft copy of the VAPP law and prepare the flex for VAPP law at TOAN. He also shared communications plan for the SAVE project

- Sanctualization of SAVE post on social so that it gets a lot of traffic.

- Specific toll free line for reporting, tracking cases ( since issues are not addressed by Youth Alive Foundation there could be a backlash because Youth Alive Foundation do not address Gender Base Violence but refer cases to partners).

- A weekly post should be made ( People get tired of reading long post rather a short video would  suffice).

- Radio or videos or drama should be used for VAPP law.

Chico also shared updates of the invitation by NDLEA on the 26th and 27th of march which Nonso attended. He also added that he had shared the VAPP law comic with the management and was he was asked by management to simplify the comic. Furthermore on the 25th of April 25 advocates were inaugurated by the Governor’s wife for gender base violence at the Governor’s Office having members of civil organizations, ministry of justice and security agencies were present. A new book was given on the training of secondary schools on VAPP law.

Onyeka assigned Chico to prepare a Radio jingle and Drama, and  the studio should be used for the production.

Chico gave a report of a reported case of domestic violence. A police officer called to report a case of domestic violence whose husband is a journalist. He abuses his wife and has cutlass under the bed and other places in the house which he uses on the woman. She was taken to to the ministry of justice and a case file was opened for her.

Updates on SDN:  David shared updates in the meeting of his conversation with Onuks of Roothub for packages and services which can be used for the EU project since they are technical partners of. Kingsley also called to confirm which packages could be used for the Women in business which included Digital skills and marketing.

Updates on Heroes Squad:  Chico shared updates on The hero squad meeting had 5 persons in attendance which was a low turn due to late communication which Chico commented that the flyers for the meeting were supposed distributed weeks ahead for the Hero meeting. Chico also expressed his displeasure at the low turnout due to the attitude of the exco’s even though they had a 2 hour meeting after they were inaugurated.

Onyeka added that Nonso needs follow up more closely, because he looks like someone who needs to be pushed, Ebidi should do more on Heroes Squad while Nonso may be a figure head or plan B. She also added that Chico should push the team to know their plans before they have their meeting.

Updates on SCALE:

Onyeka updated the team of the upcoming Cluster Coaching on the 11th and 12th May 2, 2023 theme “The Arise Agenda Opportunity For Youth Entrepreneurship and Employment” . ED is coming on the 9th, David should make a reservation at Watbridge hotel and reach out to Peace to confirm the number of people we are to book for. Compile our list and send mails to organizations we are inviting. Venue: Havilla Hall.

Updates on EU PROJECT:

Onyeka gave the update on Bridging Digital Gender Gap. 500 women to participate for 3 months digital skills training .

David also added that Opara asked him to send 24 local government and 2 extra communities. He also complained that the costing doesn’t make sense and his people in the field are also complaining of the same thing.

TASK

Onyeka

1. Number of persons attending and for food.

2. Work with David to get questions to send to Dr Uduak for the Cluster Coaching event.

3.Send E.U project report today.

4. Go to Havilla hotel a day before the event to check the hall for Sound (mic), refreshment and capacity.

5.  Engage with Peace for photography.

David:

1.Print flex for learning event.

2.Ensure Flier for the learning event and ensure that the post is boosted with a registration link.

3.Call Dr to draw up agenda for cluster coaching and Moderate the event.

4. Manage the guest to ensure they come on time.

5. Collect questions from People during the event.

Future

1.Get Biro for registration.

2. Get the printer to Havilla Hotel.

Emmanuel

1.Take important quotes or key note during the Cluster coaching

2. Make calls for cluster Coaching today.

3.Work with Chico to air jingles

Chico

1.Work with Emmanuel on Airing Jingles

2. Get volunteers to attend the learning cluster coach and learning event.

Konom

1.Work with Victory and Future to usher during the event.

2. Go to Havilla hotel a day before the event to check the hall for Sound (mic), refreshment and capacity.

AOB

Chico gave an update of a woman came to ask for land to farm. She pleaded that the land should be given for 8,000 naira for two years but Mr Chico responded that the land is for 10,000 naira for now.